## Slide 1: Where we really are against the Sep 28 roadmap
STATUS RECONCILIATION · WEEK 4 OF PHASE 0
Build is ahead of plan. Data and production readiness are behind. Recommended: pull the pilot forward where the evidence supports it, and put the effort into the gates.
Prepared by Wolf & Co. for Leader · Oct 19, 2026

## Slide 2: About six weeks ahead on build, behind on the gates
THE BOTTOM LINE
12
recons trained in the platform
Fed + 11 monthly. The plan had no template build until Nov 23.
9 / 12
tie on two months of history
The 3 breaks trace to errors in Leader's own workpapers.
24
Leader recon forms in hand
12 left to train. Matches the Jan 12 committed minimum.
2 days
of Fed history received
Both month-ends. The plan assumed 2–3 months of daily data.
0
production environments
The app runs on a dev workstation. Nov 9 parallel run needs one.
What this means: template build was supposed to be the hard part, and it isn't. The critical path has moved to what the plan treated as housekeeping: Fed daily data, a production environment, and Leader's sign-off on variances in their own figures. Keep Nov 23 and May 25. Pull the pilot forward. Spend the time we've saved on the gates.

## Slide 3: Roadmap scorecard
PLAN VS ACTUAL · AS OF OCT 19
Workstream | Plan said, by now | Where we are | Status
Kickoff & data requests | Sep 28 – Oct 2: owners confirmed, samples requested | Leader's original file set received; Fed is the only daily recon in it | On track
Sizing sprint | By Oct 9: sample 40–50 recons, test the type-to-instance ratio | 24 forms sampled. Pattern holds: one LIP form covers 6 GL accounts, FHLB covers 2 | Partial
Full 600+ inventory | Oct 5 – 23: working sessions with every recon owner | No evidence of the 600+ inventory in delivery records. Confirm before the Nov 6 sign-off | Not evidenced
Fed: scope & samples | By Oct 23: sample Fed and GL files, layout agreed | Done. Uses the trial balance as the ledger, as Leader's preparer does | Ahead
Fed: configure & back-test | Oct 26 – Nov 6, on 2–3 months of daily history | Configured; ties to zero on both days. Only 2 month-end days exist to test on | Ahead, thin data
Environment & upload intake | Oct 19 – Nov 6: minimal production environment | Dev workstation only; the API stops when the session ends. Hosting not chosen | Behind
Pilot templates | Nov 23 – Dec 4: build ~5 types | 11 monthly recons built and back-tested on Jul and Aug | ~6 wks ahead
Security | Close security review in Phase 1 | API keys still readable in Bitbucket history; rotation pending | Behind

## Slide 4: Twelve recons in, three lessons for the plan
WHAT THE BUILD TAUGHT US
Recon | Months | Result
Fed (daily) | Jan, Feb | Ties both
FHLB Ideal Way | Jul, Aug | Ties both
FHLB Stock | Jul, Aug | Ties both
Investments | Jul, Aug | Ties (in rounding)
Loan Suspense | Jul, Aug | Ties both
Other Serviced | Jul, Aug | Ties both
SBL | Jul, Aug | Ties (in rounding)
LIP 1210400 | Jul, Aug | Ties both
LIP 2800310 | Jul, Aug | Ties both
Deferred Fees | Jul, Aug | Jul breaks: stale GL 5,157.50
CDARS | Jul, Aug | Breaks: wrong sign
Loan Recon | Jul, Aug | Breaks: misclassified accts
The breaks are Leader's errors, not ours
A stale GL figure, a sign typed backwards, and account misclassifications that Leader's own subledger report prints. The gate needs a defined path for customer-side variances, or sign-off stalls on figures we can't fix.
Real installs find gaps that validation can't
Four engine gaps only showed up on live ingests: a credit-column reader, a split item block, undated items, and module linking. All are fixed and tested. Budget 1–2 days per new type for reader work.
Types × instances is real at Leader
Six LIP GL accounts share one form and two FHLB recons share a pattern. That supports the ~18-type estimate, but the 600+ count itself hasn't been tested.

## Slide 5: Bank the build lead, pull the pilot forward, keep the end date
RECOMMENDATION · MID-LEVEL AGGRESSIVE
Pull forward
Train all 24 Leader forms by Nov 6, not Dec 4
New early release on Tue Dec 8: ~10 monthly recons live, run in parallel on the October close
Raise the Jan 12 committed minimum from 24 to 36 recons; the ~60 target stays
Hold, with conditions
Fed live Mon Nov 23, if ≥10 ordinary weekdays of Fed and GL files arrive by Oct 30
If they don't arrive by Nov 6, Fed moves to Tue Dec 1. No other date moves with it
Phase 0 sign-off stays Nov 6, but only with the 600+ inventory evidenced
Add to the plan
Rotate the exposed API keys by Oct 23, ahead of any security review
Hosting decision Oct 30; production environment ready Nov 6
A customer-side variance path in the promotion gate: Leader corrects or accepts each break
Leave alone
Wave 2 on Feb 9 and the two-week cadence
May 25 for all ~600; re-baseline at Nov 6 as planned
The self-service ladder and its stability gate

## Slide 6: Revised milestone calendar to the pilot
NEAR-TERM DATES · CHANGES HIGHLIGHTED
Date | Original plan | Revised | Change
Fri Oct 23 | Fed and GL samples; layout agreed | Done Oct 19. Rotate exposed keys; send Leader the Fed questions and the 3 breaks | Done
Fri Oct 30 | 2–3 months of Fed history | ≥10 ordinary weekdays of Fed + GL; trial balance pull timing; hosting decision | Changed
Fri Nov 6 | Phase 0 sign-off | Sign-off with the inventory evidenced; all 24 Leader forms trained; production environment up | Earlier
Mon Nov 9 | Fed parallel run starts | Unchanged. Runs on the production environment, not a workstation | Same
Fri Nov 20 / Mon Nov 23 | Fed gate / Fed live | Unchanged. Fallback Tue Dec 1 if daily data misses Nov 6 | Same
Tue Dec 8 | No milestone | Early release: ~10 monthly recons live after parallel on the October close | New
Fri Dec 18 | Pilot UAT complete | Unchanged. Holiday freeze Dec 21–25 | Same
Tue Jan 12 | Pilot: 24 minimum, ~60 target | Pilot: 36 minimum, ~60 target | Raised
Wave 2 (Feb 9) through Wave 9 (May 25) are unchanged until the Nov 6 re-baseline. Dec 8 sits after November's close window (business day 6).

## Slide 7: The risks have moved from build to readiness
RISK REGISTER, UPDATED
No production environment
New · High
Nov 9 parallel run and Nov 23 go-live both need it. Today the API stops when a session ends.
Action: Hosting decision Oct 30; environment ready Nov 6
Owner: Wolf engagement lead
Fed daily data is two month-end days
New · High
Daily behaviour is untested. Trial balance timing decides whether backdated entries create false breaks.
Action: ≥10 weekdays by Oct 30; Dec 1 fallback
Owner: Leader Fed owner
Exposed credentials in repo history
New · High
Old Anthropic and AWS keys are readable in Bitbucket. This would fail any security review.
Action: Rotate and revoke by Oct 23
Owner: Wolf data engineer
600+ inventory not evidenced
New · Med
Wave sizing from Feb onward rests on a count nobody has checked.
Action: Show inventory progress at the Oct 30 steering
Owner: Finance ops lead
Gate stalls on Leader-side breaks
New · Med
Three of twelve recons break on Leader's own figures. Sign-off waits on Leader correcting them.
Action: Customer-side variance path; 5-day turnaround
Owner: Leader recon owners
Template build effort
Lowered
Was the implicit main risk. 12 built and tested in weeks, with 4 engine gaps found and closed.
Action: Keep 1–2 days per type for reader work
Owner: Wolf recon architect

## Slide 8: Asks and owners
THIS WEEK AND NEXT
From Leader
By Oct 30: ten or more ordinary weekdays of Fed statements and GL exports, not month-ends
On a normal day, is the trial balance pulled the same day or the next morning?
February's FedACH settlement summary is dated Feb 26. Is that intended?
Confirm or correct the 3 breaks: Deferred Fees July (GL 1300310 stale by 5,157.50), CDARS signs, Loan Recon misclassifications
Where the 600+ inventory stands, before the Nov 6 sign-off
From Wolf & Co.
Oct 23: rotate and revoke the exposed Anthropic and AWS keys
Oct 30: hosting decision; production environment ready by Nov 6
Nov 6: train the remaining 12 forms: SLIP, Ramp, Escrow, Narmi, Deposit, DDA, Deferred Tax Asset, Loan Accrued Interest, and LIP 1210150, 1609500, 2202500, 2800550
Before Dec 8: per-month upload checklist and the question layer, so owners can run uploads themselves
Write the customer-side variance path into the promotion gate