## Slide 1: Finish the types, then let the platform carry the rollout
REVISED ROLLOUT STRATEGY · LEADER
Twelve recons in, building types is no longer the hard part. We stop hand-configuring 600 recons, finish the type library, and build feedback, gating and fast setup into the platform so Leader can roll out at their own pace.
Prepared by Wolf & Co. · Oct 19, 2026 · Replaces the services-led wave plan

## Slide 2: The roadmap planned for a problem we no longer have
WHY CHANGE THE PLAN
12
recons trained
Fed + 11 monthly, weeks before the plan's first template build on Nov 23.
9 / 12
tie on history
Two months each. The matching itself is not where the risk is.
3
breaks, all Leader's
A stale GL figure, a sign typed backwards, and misclassified accounts.
24
forms ≈ the type library
The roadmap estimated ~18 types behind the 600+. One LIP form covers 6 GL accounts.
The roadmap's labor model assumed two things: building types would be hard, and self-service didn't exist. So it had Wolf & Co. hand-configuring ~40 recons per wave through April, with Leader earning independence step by step until Wave 6. Neither assumption holds. That effort belongs in the platform, where it compounds, rather than in our hours, where it doesn't.

## Slide 3: From services-led waves to a platform-led rollout
WHAT CHANGES
 | Roadmap (Sep 28) | Platform-led (proposed)
Who sets up recons | Wolf & Co., ~40 per wave, tapering only from Wave 3 | Leader's owners, from the Jan 12 pilot
How we learn | Our people beside theirs, wave by wave | In-app feedback on every result, sorted into buckets and routed to us
Promotion gate | A meeting and a checklist per wave | Built into the platform: ties to signed figures, every variance labeled, sign-off recorded
Inventory | Working sessions with every recon owner | Owners tag each of their 600 recons with one of the 24 types, or "doesn't fit"
Self-service | A five-month ladder; independent from Apr 13 | The default from day one; we review what gets flagged, not every recon
Our time goes to | Configuring instances | Types, reader gaps, setup tooling and the feedback loop
End date | All ~600 by May 25 | All ~600 in March, if setup time per recon comes down (see slide 7)

## Slide 4: Types first, then the platform does the scaling
THE PLAN IN FOUR MOVES
1
By Nov 6
Finish the type library
Train the remaining 12 forms: SLIP, Ramp, Escrow, Narmi, Deposit, DDA, Deferred Tax Asset, Loan Accrued Interest and four LIP forms.
2
By Nov 6
Map the 600 to types
Each owner tags their recons with one of the 24 types or "doesn't fit". A few hours each, and the only proof that 24 types really is enough.
3
Nov – Dec
Build the loop into the platform
A "this result is wrong" action, the gate as a feature, the upload checklist, the question layer and setup tooling.
4
From Jan 12
Leader rolls out
Owners set up their own recons. We fix what the loop sends us and ship it back into the platform.
The blockers don't change with the strategy. Fed daily data, a production environment and rotating the exposed keys are still on the critical path (slide 8).

## Slide 5: Every wrong result Leader flags makes the next recon better
HOW THE PLATFORM GETS SMARTER
Leader flags a result
"This result is wrong" on any recon, with a note and the file.
Platform sorts it
It suggests a bucket from the evidence; a reviewer confirms it.
Leader's data error
Back to the recon owner to correct. Like the 3 breaks so far.
Leader
Reader gap
A file layout we can't read yet. Like 2 of the 4 engine gaps.
Wolf & Co.
Rule gap
Tolerance, sign or matching logic is wrong for this recon.
Wolf & Co.
New type
Doesn't fit any of the 24. Added to the library.
Wolf & Co.
Fixes ship to every recon of that type
A reader or rule fix is tested against every tied recon of that type before release, then the flagged recon re-runs. One report improves every recon of that type, not just one.
Only the last three buckets cost us time. The share of flags that are Leader's own data errors is the measure of how mature the platform is.

## Slide 6: Guardrails that make this safe for a bank
WHAT FEEDBACK WON'T CATCH
False ties are silent
Leader will report a false break because someone sees it. Nobody reports a recon that wrongly ties.
Guardrail: Every recon ties to the preparer's signed figure over at least two periods before it goes live, and is spot-checked after.
Setup may not be point-and-click
Two of the four engine gaps came from new file layouts. If exports vary by recon, those come back to us.
Guardrail: Have three owners set up recons unaided in December to measure it, before we commit to the January volumes.
Self-service needs maker-checker
In a bank, whoever sets up a recon can't also approve it into production.
Guardrail: Separate roles for setting up and approving, with the audit trail and version history the roadmap already promised.
The gate stays, as a feature
Self-service never means ungoverned. It means the platform enforces the gate, not a meeting.
Guardrail: The gate is a hard block in the app: back-test ties, every variance labeled, sign-off recorded.

## Slide 7: Setup time per recon now decides the end date
THE NEW LIMIT IS LEADER'S HOURS
Chart: Weeks of owner time to set up all 600 recons
| 2 hours (roadmap) | 1 hour | 30 minutes
Weeks to set up all 600 | 13.3 | 6.7 | 3.3
600 recons ÷ six owners at 15 hrs/week (90 hrs/week). Excludes uploads and sign-off.
Product work that cuts setup time
Suggest field mappings from the uploaded file, so owners confirm rather than map
Clone setup from a similar recon (one LIP form covers six GL accounts)
A per-month upload checklist, so owners know what's due and what's missing
The question layer, so owners get answers in the app instead of from us
Measure real setup time from the first recons Leader sets up themselves
Ask Leader before committing: can all six owners give ~15 hrs/week from January?

## Slide 8: Fewer of our hours, earlier finish
REVISED MILESTONES
Date | Milestone | Lead
Fri Oct 23 | Rotate the exposed keys. Send Leader the Fed questions and the 3 breaks | Wolf & Co.
Fri Oct 30 | ≥10 ordinary weekdays of Fed + GL files. Hosting decision. Owners start tagging the 600 | Leader / Wolf
Fri Nov 6 | Type library complete (24 forms). 600 mapped to types. Production environment up. Steering sign-off | Both
Mon Nov 23 | Fed live (gate Nov 20). Falls back to Dec 1 if the daily data misses Nov 6 | Both
Fri Dec 4 | Feedback action and in-app gate live. Three owners set up recons unaided, timed | Wolf & Co.
Tue Dec 8 | Early release: ~10 monthly recons live after a parallel run on the October close | Both
Tue Jan 12 | Pilot: Leader sets up their own recons. Floor of 36; size set by upload readiness | Leader
Feb – Mar | Leader-led rollout; we work the feedback queue. All ~600 in March if setup is ≤1 hr each | Leader
Replaces the Wave 2–9 plan. May 25 becomes the outer limit, not the target.

## Slide 9: What we need to agree to go this way
DECISIONS NEEDED
Adopt the platform-led plan
Replaces the services-led waves. Wolf & Co. effort moves from setting up recons to the platform.
Owner: Wolf & Co. leadership
Rework the commercial model
The roadmap was a services proposal. If pricing assumed our setup hours, it needs to change with the plan.
Owner: Wolf & Co. leadership
Leader owner time from January
Six owners at ~15 hrs/week. Most of the timeline depends on it.
Owner: Leader sponsor
Platform build priorities for Nov – Dec
Feedback action, in-app gate, maker-checker, mapping suggestions, clone-from-similar, upload checklist.
Owner: Product